## data
Agents | Teams | Programmes | Tâches | Missions | Date de début | Date de fin | Types | Couleurs | Jalons | Formes | Taille des Formes | Etiquettes | Taille | Avancement
Agent Alpha | Research Team | Program 1 | Concept Phase | Initial Benchmarking | 2025-01-01 | 2025-03-01 | Research | #800020 | 0 |  | 500 | 1 | 0.6 | 0.88347
Agent Alpha | Research Team | Program 1 | Concept Phase | Technical Study | 2025-03-02 | 2025-05-30 | Research | #800020 | 0 |  | 500 | 2 | 0.3 | 0.50361
Agent Alpha | Innovation Lab | Prototype Dev | Prototype 1 | Rapid Prototyping | 2025-05-15 | 2025-06-30 | Development | #00008B | 0 |  | 500 | 3 | 1 | 0.37188
Agent Alpha | Innovation Lab | Prototype Dev | Prototype 2 | Internal Test | 2025-07-15 | 2025-09-15 | Testing | #095228 | 0 |  | 500 | 4 | 0.8 | 0.4315
Agent Alpha | Innovation Lab | Program 2 | Review | Prototype Review | 2025-10-01 | 2025-10-01 | Milestone | #FFD700 | 1 | M -0.05 -0.25 L -0.05 0.05 L -0.05 0.35 L 0 0.35 L 0 0.05 L 0.25 -0.1 L 0 -0.25 L -0.05 -0.25 | 5000 | 5 | 1 | 0.94872
Agent Alpha | Innovation Lab | Program 3 | Industrialization | Pilot Tests | 2025-10-15 | 2026-02-01 | Development | #00008B | 0 |  | 500 | 6 | 0.4 | 0.55891
Agent Alpha | Innovation Lab | Industrialization | Certification | Final Approval | 2026-02-01 | 2026-02-01 | Milestone | #FFD700 | 1 | circle | 500 | 7 | 1 | 0.79657
Agent Bravo | Operations Unit | Deployment | Phase 1 | System Rollout | 2025-01-01 | 2025-04-01 | Operations | #708090 | 0 |  | 500 | 8 | 0.3 | 0.65406
Agent Bravo | Operations Unit | Deployment | Phase 2 | Performance Optimization | 2025-03-15 | 2025-06-15 | Operations | #708090 | 0 |  | 500 | 9 | 0.5 | 0.55715
Agent Bravo | Maintenance Division | Maintenance | Cycle 1 | Maintenance Window | 2025-07-01 | 2025-08-01 | Maintenance | #2F4F4F | 0 |  | 500 | 10 | 0.7 | 0.32037
Agent Bravo | Maintenance Division | Maintenance | Cycle 2 | Audit & Inspection | 2025-09-01 | 2025-09-30 | Maintenance | #2F4F4F | 0 |  | 500 | 11 | 0.9 | 0.63655
Agent Bravo | Operations Unit | Upgrade | Planning | Upgrade Planning | 2026-01-15 | 2026-02-20 | Operations | #708090 | 0 |  | 500 | 12 | 1 | 0.81129
Agent Bravo | Operations Unit | Upgrade | Execution | Deployment Execution | 2026-03-01 | 2026-06-01 | Operations | #708090 | 0 |  | 500 | 13 | 0.8 | 0.84178
Agent Charlie | QA Team | Quality Cycle | Cycle A | Software Validation | 2025-02-01 | 2025-04-01 | Testing | #095228 | 0 |  | 500 | 14 | 0.6 | 0.43309
Agent Charlie | QA Team | Quality Cycle | Cycle B | Hardware Validation | 2025-03-15 | 2025-05-15 | Testing | #095228 | 0 |  | 500 | 15 | 0.5 | 0.59267
Agent Charlie | QA Team | Field Trials | Trial Round 1 | Field Deployment | 2025-07-01 | 2025-08-15 | Testing | #095228 | 0 |  | 500 | 16 | 0.3 | 0.41189
Agent Charlie | QA Team | Field Trials | Trial Round 2 | User Feedback | 2025-10-01 | 2025-11-20 | Testing | #095228 | 0 |  | 500 | 17 | 0.4 | 0.70487
Agent Charlie | QA Team | Final Review | Certification | Approval Audit | 2026-01-10 | 2026-03-10 | Testing | #095228 | 0 |  | 500 | 18 | 0.8 | 0.94665
Agent Charlie | QA Team | Final Review | Certification | Certification Milestone | 2026-03-10 | 2026-03-10 | Milestone | #FFD700 | 1 | diamond | 500 | 19 | 1 | 0.48196